## Training Plan
Sr.No | Topic | Activities | Duration | Start Date | End date | Links
1 | Xamarin.Forms Docs | Setup | 2 days | 2021-04-27 | 2021-04-28 | https://docs.microsoft.com/en-us/xamarin/get-started/installation/?pivots=windows
|  | Introduction to Xamarin |  |  |  | https://docs.microsoft.com/en-us/xamarin/get-started/what-is-xamarin-forms
|  | Xamarin.Forms |  |  |  | https://docs.microsoft.com/en-us/xamarin/cross-platform/app-fundamentals/
|  | Architecture |  |  |  | https://docs.microsoft.com/en-us/xamarin/get-started/first-app/?pivots=windows
How Xamarin works?
PCL vs SAP vs .Net Standard
|  | Introduction to XAML | 1 day | 2021-04-29 | 2021-04-29 | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/xaml/xaml-basics/get-started-with-xaml?tabs=windows
|  | XAML Basics |  |  |  | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/xaml/xaml-basics/essential-xaml-syntax
|  | XAML Markup Extensions | 1 day | 2021-04-30 | 2021-04-30 | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/xaml/xaml-basics/xaml-markup-extensions
|  | XAML Data Bindings |  |  |  | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/xaml/xaml-basics/data-binding-basics
|  | Application class and app life cycle | 1 day | 2021-05-03 | 2021-05-03 | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/app-fundamentals/application-class
|  | Dependency Service |  |  |  | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/app-fundamentals/app-lifecycle
|  | User Interface Controls - part1 | 2 days | 2021-05-04 | 2021-05-05 | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/app-fundamentals/dependency-service/
|  | User Interface Controls - part2 |  |  |  | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/user-interface/
|  | Resource Dictionary | 1 day | 2021-05-06 | 2021-05-06 | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/xaml/resource-dictionaries
|  | Styles |  |  |  | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/user-interface/styles/
|  | Layouts | 1 day | 2021-05-07 | 2021-05-07 | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/user-interface/controls/layouts
|  | Xamarin Essential Package | 1 day | 2021-05-10 | 2021-05-10 | https://docs.microsoft.com/en-us/xamarin/essentials/?context=xamarin/xamarin-forms
|  | Behaviours | 1 day | 2021-05-11 | 2021-05-11 | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/app-fundamentals/behaviors/
|  | Effects |  |  |  | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/app-fundamentals/effects/
|  | Triggers | 1 day | 2021-05-12 | 2021-05-12 | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/app-fundamentals/triggers
|  | Gestures |  |  |  | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/app-fundamentals/gestures/
|  | Templates | 1 day | 2021-05-13 | 2021-05-13 | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/app-fundamentals/templates/
|  | Custom Renderers | 1 day | 2021-05-14 | 2021-05-14 | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/app-fundamentals/custom-renderer/
|  | MVVM Design Pattern | 1 day | 2021-05-17 | 2021-05-17 | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/enterprise-application-patterns/mvvm
2 | Build Android Apps for Absolute beginner(Udemy) | Xamarin elements | 1 day | 2021-05-18 | 2021-05-18
|  | Simple calculation App | 1 day | 2021-05-19 | 2021-05-19
3 | Build Native Cross Platforms apps with C#(Udemy) | Getting Started and XAML Essentials | 1 day | 2021-05-20 | 2021-05-20
|  | Layouts and Images | 1 day | 2021-05-21 | 2021-05-21
|  | Lists and Navigations | 1 day | 2021-05-24 | 2021-05-24
|  | Forms and Setting Pages & Data Access | 1 day | 2021-05-25 | 2021-05-25
|  | MVVM and Beyond Basics | 1 day | 2021-05-26 | 2021-05-26
4 | Complete Xamarin Developer Course iOS and Android(Udemy) | Hello world with Xamarin.forms | 1 day | 2021-05-27 | 2021-05-27
|  | XAML & navigation Travel record app | 1 day | 2021-05-28 | 2021-05-28
|  | C# Fundamentals | 1 day | 2021-05-31 | 2021-05-31
|  | Sqlite Local databases | 1 day | 2021-06-01 | 2021-06-01
|  | Maps & Location | 1 day | 2021-06-02 | 2021-06-02
|  | REST | 1 day | 2021-06-03 | 2021-06-03
Working with Images
Linq
|  | Azure Services | 1 day | 2021-06-04 | 2021-06-04
|  | MVVM | 1 day | 2021-06-07 | 2021-06-07
|  | Storing Images in cloud | 1 day | 2021-06-08 | 2021-06-08
|  | Hello world Xamarin Native | 1 day | 2021-06-09 | 2021-06-09
|  | Delivery App login - Android | 1 day | 2021-06-10 | 2021-06-10
Delivery App Login - iOS
|  | Azure app services | 1 day | 2021-06-11 | 2021-06-11
Sharin code
|  | Tabs in Android & iOS | 1 day | 2021-06-14 | 2021-06-14
Lists in Android & iOS
|  | Delivery persons app | 1 day | 2021-06-15 | 2021-06-15
|  | Adding platforms specific funtionality | 1 day | 2021-06-16 | 2021-06-16
Publishing on app stores
In-App purchases
5 | Deployment and Testing | Testing | 1 day | 2021-06-17 | 2021-06-17 | https://docs.microsoft.com/en-us/xamarin/xamarin-forms/deploy-test/
|  | Deployment | 1 day | 2021-06-18 | 2021-06-18
|  | Microsoft learn modules | 1 day | 2021-06-21 | 2021-06-21
|  | Total | 40 days